## 220_E
Darbų įkainiai / Work Rates
Nr. / No. | Aprašymas / Description |  | Sąnaudų žiniaraščio žymuo TP ar DP / BoQ list name from TDD or DDD | Mato vnt. / Unit | Kiekis / Quantity | Darbų atlikimas / Work progress % | Balance / Likutis | Montavimas ir paleidimas (darbai + surinkimo medžiagos + protokolai) / Installation and commissioning (works + assembly materials + protocols) | Medžiagos / Materials | Bendrai (darbai + medžiagos) / Total (work+material) | Komentarai / Įrengimo kiekis statybvietėje / Comment / Installation amount on site | Yra sandėlyje / Available on storage
ELECTRICAL E - Cable routes / Kabelinės trasos
862 | Kabelių loveliai su montavimo elementais ir kt. (išskyrus laikiklius, horizontalius/vertikalius lenkimus, kanalus, sijas, dangčius, trišakius ir susikirtimus) / Cable trays with installation element, etc. (except brackets, horizontal/vertical bends, channels, bars (beams), covers, tees and cross-overs) | plotis / width 100 mm, aukštis / height 100 mm arba lygiavertis/or equivalent | VKJ01-220-DP-E-10.7797 | m | 283 | 70 | 84.9 | 40 | 35 | 6367.5 | due to missing documentation, total length and types of components were assumed | *
863 | Kabelių loveliai su montavimo elementais ir kt. (išskyrus laikiklius, horizontalius/vertikalius lenkimus, kanalus, sijas, dangčius, trišakius ir susikirtimus) / Cable trays with installation element, etc. (except brackets, horizontal/vertical bends, channels, bars (beams), covers, tees and cross-overs) | plotis / width 200 mm, aukštis / height 100 mm arba lygiavertis/or equivalent | VKJ01-220-DP-E-10.7797 | m | 307 | 70 | 92.1 | 40 | 38.5 | 7229.85 | due to missing documentation, total length and types of components were assumed | *
864 | Kabelių loveliai su montavimo elementais ir kt. (išskyrus laikiklius, horizontalius/vertikalius lenkimus, kanalus, sijas, dangčius, trišakius ir susikirtimus) / Cable trays with installation element, etc. (except brackets, horizontal/vertical bends, channels, bars (beams), covers, tees and cross-overs) | plotis / width 300 mm, aukštis / height 100 mm arba lygiavertis/or equivalent | VKJ01-220-DP-E-10.7797 | m | 118 | 56 | 51.92 | 40 | 43.2 | 4319.744 | due to missing documentation, total length and types of components were assumed | *
865 | Kabelių loveliai su montavimo elementais ir kt. (išskyrus laikiklius, horizontalius/vertikalius lenkimus, kanalus, sijas, dangčius, trišakius ir susikirtimus) / Cable trays with installation element, etc. (except brackets, horizontal/vertical bends, channels, bars (beams), covers, tees and cross-overs) | plotis / width 400 mm, aukštis / height 100 mm arba lygiavertis/or equivalent | VKJ01-220-DP-E-10.7797 | m | 603 | 45 | 331.65 | 40 | 50 | 29848.5 | due to missing documentation, total length and types of components were assumed | *
866 | Kabelių loveliai su montavimo elementais ir kt. (išskyrus laikiklius, horizontalius/vertikalius lenkimus, kanalus, sijas, dangčius, trišakius ir susikirtimus) / Cable trays with installation element, etc. (except brackets, horizontal/vertical bends, channels, bars (beams), covers, tees and cross-overs) | plotis / width 600 mm, aukštis / height 100 mm arba lygiavertis/or equivalent | VKJ01-220-DP-E-10.7797 | m | 39 | 0 | 39 | 45 | 75.2 | 4687.8 | due to missing documentation, total length and types of components were assumed | *
867 | Kabelių loveliai su montavimo elementais ir kt. (išskyrus laikiklius, horizontalius/vertikalius lenkimus, kanalus, sijas, dangčius, trišakius ir susikirtimus) / Cable trays with installation element, etc. (except brackets, horizontal/vertical bends, channels, bars (beams), covers, tees and cross-overs) | - | VKJ01-220-DP-E-10.7797 | m | 60 | 80 | 12 | 45 | 75.2 | 1442.4 | due to missing documentation, total length and types of components were assumed | *
868 | Papildomos surinkimo medžiagos įrangos montavimui/ Additional assembly materials for equipment installation | - | VKJ01-220-DP-E-10.7797 | kg | 445 | 50 | 222.5 | 10 | 10 | 4450 | due to missing documentation, total length and types of components were assumed | *
[8 empty] | Viso: / Total: |  | 58345.794
Remarks:Material, installation and connection prices must be given to all items mentioned in the list
Pastabos: Medžiagų, montavimo ir prijungimo darbų kainos turi būti nurodytos visoms sąraše nurodytoms pozicijoms
* Informations concerning the total quantities of available materials are in "Stored deliveries" - Appendix 1E
* Informacija apie bendrą turimų medžiagų kiekį pateikiama dokumente „Stored deliveries“ - 1E priedas