Annex No. 6 to SPC

TERMS AND CONDITIONS OF DIRECT SETTLEMENT WITH SUB-SUPPLIERS

In case the Sup-Supplier intends to make use of the possibility of direct settlement, the Supplier shall undertake to enter into a tripartite agreement between the Supplier, the Contracting Authority and the Sub-Supplier, which shall establish the procedure of direct settlement, including the following conditions:

1. Advance payment shall not be applicable to the Sub-Supplier.

2. The amount of each interim payment shall be determined in accordance with the number of actually transferred goods/ provided services/ completed works and the value thereof.

3. Before providing the payment documents to the Contracting Authority, the Sub-Supplier shall submit the properly executed Procurement contract execution documents to the Supplier for approval (the note on transfer and acceptance of the transferred goods/ provided services/ completed works and/ or etc.) in 3 (three) copies.

4. The Procurement contract execution documents provided by the Sub-Supplier shall be deemed duly executed and submitted, provided that the information provided in the above documents on goods transferred/ services provided/ works completed by the Sub-Supplier is correct and transferred goods/ provided services/ completed works as well as execution of the documents complies with the terms and conditions of the Procurement contract.

5. Having received the Procurement contract execution documents from the Sub-Supplier, the Supplier shall verify them and having determined that the information presented in the documents about goods transferred/ services provided/ works completed by the Sub-supplier is correct and transferred goods/ provided services/ completed works comply with the terms and conditions of the Procurement contract, the submitted documents submitted have been executed properly,  not later than within 3 (three) working days from the date of reception of such documents, the Supplier shall:

5.1. sign and ratify the note on transfer and acceptance of the transferred goods/ provided services/ completed works;

5.2. submit the Procurement contract execution documents to the Contracting Authority.

6. In case the Supplier determines that the Procurement contract execution documents submitted by the Sub-supplier were executed improperly, the information provided in the documents about the transferred goods/ provided services/ completed works is incorrect, the transferred goods/ provided services/ completed works are not in compliance with the terms and conditions of the Procurement contract or in case of other incompliances, the Supplier shall notify the Sub-supplier in written not later than within 5 (five) working days from the day when such a decision was made, indicating the shortcomings and determining a reasonable term for eliminating the shortcomings.

7. After the Sub-Supplier has eliminated the shortcomings within a period established by the Supplier, the Supplier following the established procedure shall repeatedly verify the documents and provide them to the Contracting Authority, having signed and approved.

8. Not later than within 5 working days from the day of reception of Procurement contract execution documents the Contracting Authority shall verify the submitted documents and, provided that the Supplier implements all the contractual liabilities properly and on time and the provided documents were executed properly, the information provided in the documents about the transferred goods/ provided services/ completed works is correct, the transferred goods/ provided services/ completed works are in compliance with the terms and conditions of the Procurement contract, shall sign the note on transfer and acceptance of the transferred goods/ provided services/ completed works and other documents, if applicable, shall also submit the signed documents (1 (one) copy for both) Supplier and Sub-supplier.

9. In case the Contracting Authority determines, that the documents submitted by the Supplier have been executed improperly, not all the documents were submitted or the information provided in the documents about the transferred goods/ provided services/ completed works is incorrect, transferred goods/ provided services/ completed works are not in compliance with the terms and conditions of the Procurement contract or in case of other incompliances, not later than within 5 (five) working days from the day when such a decision was made, the Contracting Authority shall notify the Supplier in written, indicating the shortcomings and determining a reasonable term for elimination of the shortcomings.

10. After the Supplier eliminates the shortcomings and corrects the documents within the term established by the Contracting Authority, the Contracting Authority not later than within 3 (three) working days from the date of receipt of all properly executed documents shall sign the note on transfer and acceptance of transferred goods/ provided services/ completed works and other documents, if applicable, and shall submit the signed documents to the Supplier and the Sub-Supplier.

11. Only upon receiving the note on transfer and acceptance of the transferred goods/ provided services/ completed works fully consented and signed by all the Parties without exceptions, the Sub-Supplier shall submit an invoice via the information system SABIS to the Contracting Authority (or if there is no such a possibility via email).

12. In case the Sub-Supplier submits an invoice by other means, the Contracting Authority shall have the right not to pay such invoice.

13. Once the provided electronic invoice is executed properly, the Contracting Authority shall transfer the funds to the bank account specified by the Sub-Supplier within 30 calendar days.