## Mileston plan
No. | Description | Precents from Item price | Remarks | Invoice amount | Dates not late than
0 | Pre-payment | 30% | Pre-payment may be set between 0% and 30%, as stipulated in Contract Clause No. []. The agreed-upon down payment amount shall be deducted on equal parts from the first two invoices as specified bellow. All related details must be explicitly outlined in the proposal. |  | 1 month
1 | Approved of the project documentation for all three VSR | 20% |  | From Initial amount | 3 month
2 | After the completion of the Factory Acceptance Tests (FAT) | 40% | Can be splited by items. This indexation number will be used for this and following invoces. | From indexated amount | 16 month
3 | Item is ready to Ship. | 20% | Paking list is ready and equipment ready to load on transport. Can be splited by item. | From indexated amount | 17 month
4 | Item is delivered and unloaded in nominated place | 15% | Delivery Report should be provided with invoice. Details (list of invoices and etc.)should be provided with compentetion invoice. | From indexated amount and plus compensation | 18 month
5 | Completion of Supervision Services | 5% |  | From indexated amount
Total |  | 100%
The tables below are provided as an example and will be deleted in the final document.
Example | Description | Precents from Item price | Invoice amount | note | Column1
| VSR price: | 2000000 | Prepaymeny deducted from first two invoices as example
0 | Pre-payment | 30% | 600000 | 300000
1 | Approved of the project documentation for all three VSR | 20% | 100000
2 | After the completion of the Factory Acceptance Tests (FAT) | 40% | 596000 | 1.12 | Index
3 | Item is ready to Ship. | 20% | 448000
4 | Item is delivered and unloaded in nominated place | 15% | 336000
5 | Completion of Supervision Services | 5% | 112000
Total |  | 100% | 2192000
Example | Description | Precents from Item price | Invoice amount | note | Column1
| VSR price: | 2000000 | Example in case of no prepayment
0 | Pre-payment | 0% | 0 | 0
1 | Approved of the project documentation for all three VSR | 20% | 400000
2 | After the completion of the Factory Acceptance Tests (FAT) | 40% | 896000 | 1.12 | Index
3 | Item is ready to Ship. | 20% | 448000
4 | Item is delivered and unloaded in nominated place | 15% | 336000
5 | Ccompletion of Supervision Services | 5% | 112000
Total |  | 100% | 2192000