## Sheet1
Preliminarus darbų atlikimo grafikas
Projektas: Bitumo vamzdyno į krantinę Nr.1-1 tiesimo darbai. I etapas – konstrukcijų ir technologijos dalis
Dalis: I etapas
Darbų pavadinimas |  | Darbų atlikimo terminas (mėn.)
|  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Sutarties pasirašymas
2 | GB atramų įrengimas
3 | Vamzdynų atramų įrengimas, esamų atramų stiprinimas
4 | Technologinio vamzdyno įrengimas
5 | Vamzdyno šildymo sistemos įrengimas (atliekama kitu pirkimu)
6 | Vamzdyno šilumos izoliacijos įrengimas ir skardinimo darbai
7 | Baigiamiejo darbai, bandymi, pridavimas
Pastabos:
1. Darbų eiliškumas, darbų pradžia ir pabaiga gali būti koreguojami suderinus su Užsakovu
Užsakovas: |  | Darbų atlikimo terminas (mėn.) 2: Rangovas:
Note on C15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Simonas Dobilinskas ar tai tie max 4 mėn. stabdymo? Jei taip, kodėl grafike papiešta 3 mėn.? Ir kodėl 1 mėn. persidengia? Optimistinis scenarijus?